# Implementation Roadmap

1. Implementation Approach

The proposed improvements should be implemented in phases to reduce operational risk and allow the business to validate results at each stage.

2. Implementation Phases

| Phase | Activities | Priority | Expected Outcome |
| --- | --- | --- | --- |
| Phase 1 — Data & KPI Foundation | Improve data validation, define KPI definitions, establish cancellation reporting | High | Reliable and consistent cancellation monitoring |
| Phase 2 — Analysis & Investigation | Identify high-cancellation products, markets, periods, and high-value cancellations | High | Priority problem areas identified |
| Phase 3 — Process Improvement | Investigate potential root causes and implement corrective operational actions | High | Reduction in recurring cancellation issues |
| Phase 4 — Dashboard & Monitoring | Use Power BI for regular KPI monitoring and performance tracking | High | Continuous visibility into cancellation performance |
| Phase 5 — AI Decision Support | Use AI to summarize validated findings and support business interpretation | Medium | Faster insight generation |
| Phase 6 — Continuous Improvement | Review KPIs periodically and refine processes based on results | Medium | Sustained performance improvement |

3. Proposed Timeline

Phase 1

Data & KPI Foundation

↓

Phase 2

Analysis & Investigation

↓

Phase 3

Process Improvement

↓

Phase 4

Dashboard & Monitoring

↓

Phase 5

AI Decision Support

↓

Phase 6

Continuous Improvement

4. Key Stakeholders

- Business Management

- Business Analyst

- Operations Team

- Inventory / Fulfilment Team

- E-commerce / Sales Team

- Data / BI Team

- IT / System Team

5. Implementation Dependencies

The implementation depends on:

- Availability of reliable transaction data.

- Agreement on KPI definitions.

- Business stakeholder validation of findings.

- Availability of relevant operational teams for root-cause investigation.

- Power BI reporting access.

- Appropriate review and validation of AI-generated insights.

6. Success Measures

Implementation success can be monitored using:

- Cancellation rate.

- Cancelled transaction volume.

- Cancellation transaction value.

- High-cancellation product performance.

- High-cancellation market performance.

- Data-quality improvement.

- Regular Power BI dashboard usage.

- Effectiveness of corrective actions.

7. Risks and Mitigation

| Risk | Mitigation |
| --- | --- |
| Poor data quality | Establish data validation rules |
| Incorrect interpretation of AI insights | Require human validation |
| Lack of stakeholder adoption | Involve stakeholders during requirements and review stages |
| Root causes not visible in transaction data | Conduct additional operational investigation |
| KPI definitions differ between teams | Establish standardized KPI definitions |

8. Expected Outcome

The roadmap provides a structured path from data-quality improvement and cancellation analysis to process improvement and continuous monitoring. It enables the retailer to move from identifying cancellation problems to implementing and measuring corrective actions.